## Slide 1: Towards the coating of 3 MBB dipoles Status report
SPS-U

## Slide 2: Coating tests on MBB 096 with liner
Test #1
  Liner 2 meters, 2 cathodes, 1 anode, sputtering power 400 W (limited by geometry and arcs at the extremities)
  Thickness non homogeneous
  SEY non homogeneous as a consequence

## Slide 3: Test #1

## Slide 4: Test #1

## Slide 5: Coating tests on MBB 096 with liner
Test #2
  Liner 2 meters, 2 cathode, 2 anodes, sputtering power 700 W
  Max temperature on liner during coating 120 °C (specified for the vacuum chambers 150 °C at the sides, 300 °C on top)
  More uniform dark colour
  SEY:

## Slide 6: SEY for test #2

## Slide 7: Under way
Test #3
  Liner 2 meters, 2 cathodes, 2 anodes
  Better insulation of and shielding of feedthroughs and of cathodes extremities
  Test for higher power sputtering and temperature limit.
Cleaning of MBB 085 and MBB 040
  Si-O-Si and HC were detected on all three dipoles before cleaning
  Cleaning of MBB 096 was successful but not 100% conform to UHV specs
Modification of vacuum chambers
  Piquages on MBB 096, 085, 040 done
  Piquages to be done on MBB 51470 and QD 51510 in the tunnel (week 10, 2-6.3)
  Studs for RF shields being welded on MBB 085, 040 (MBB 096 done)

## Slide 8: Coating plans
MBB 096
  Start assembly 19.2
  Coating
  Dismount 24.2 (store under N2)
MBB 085
  Start assembly 24.2
  Coating
  Dismount 27.2 (store under N2)
MBB 040
  Start assembly 27.2
  Coating
  Dismount 4.3 (store under N2)
Last delivery date
  Monday 9.3

## Slide 9: Sample for C magnet, coated with a-C on 1.10.2008

## Slide 10: Liners
Liner #1: inox
Liner #2: a-C coated from last year
We are still testing the Zr coating parameters for the liner #3
  Problems in temperature control for obtaining the right “rough” zirconium
Liner #4 to be defined
Installation schedule to be defined both for C-magnet sample and for liners