## Sheet1
# | What | When | Mode | Time needed | Priority (1=highest)
1 | Establish low-loss 25 and 50 ns beams for LHC operation; | 50 ns: OP setup early in year 25 ns: before ecloud and scrubbing investigations | Beam setup | 2 x 12h shift | 1
2 | Dedicated scrubbing and ecloud investigations – 5 days (3+2) tentatively aimed for W13; | W13 (W14 and 15 are Easter, W16 is just before dedicated MD) | Interleaved with CNGS - some perturbation to CNGS operation to expect | 5 days | 1
3 | Higher intensity (1.4e11 for 25ns, 1.7e11 for 50 ns) studies, including I vs e [Q20 and Q26]; | Early in year for first dedicated MD block (W17?), then ongoing | Dedicated | 2x24h first MD block 1x16(24)h in subsequent MD blocks | 1
4 | ecloud mitigation measurements; | Partly in #2 (other scrubbing techniques), partly parasitic with 3, some dedicated time needed later | Parastitic + Dedicated | 2x12 h dedicated in later MD block | 1
5 | Impedance identification [Q20 and Q26]; | Early in year to avoid ions, but after full damper setup | 2 dedicated (Q20 and Q26), remainder parallel | 2x12h dedicated, numerous parallel sessions | 2
6 | TMCI limitations [Q20 and Q26]; | Early in year to avoid ions | parallel | several parallel sessions | 2
7 | Double RF system; | Early in year | Parallel | several parallel sessions | 2
8 | High bandwidth damper; | As a function of LARP and HW availabilty | Floating plus parallel | 2x12 h in floating, some parallel sessions | 2
9 | PS-SPS transfer - longitudinal and transverse; | No constraint (early check of transverse matching would be good) | Floating plus parallel | 2x12 h in floating, several parallel sessions | 2
10 | Single bunch (“space charge”) and multibunch working point optimisation [Q20 and Q26]; | Through year | Floating plus parallel | 2x12 h in floating, several parallel sessions | 1
11 | Q20: optics, damper, ultimate LHC beams, bunch length and stability, optics for fast cycles, ecloud stability, SPS to LHC transfer. | Through year - many parts covered in #3, 5, 6, 10. | Dedicated, floating and parallel | A lot. 4x16h dedicated, 4x12h floating, many parallel | 1
12 | Preservation of emittance for very low emittance beams | Early in year as precursor to operation | Dedicated and parallel (needs long injection plateau) | 2x8h dedicated shifts - also needs injection into LHC to get beams into collision | 2
13 | Tests of increasing peak RF power | Immediately before TS, in case of equipment damage | Dedicated | 2x4h | 1
14 | SPS to LHC transfer - long bunches; | Needs coordinatoon with LHC MD | Floating for setup, then LHC MD | 1x12h floating | 1