## Slide 1: LIU-SPS

## Slide 2: Mandate of LIU-SPS
Constitute a working group with a core team, define the work, coordinate activities
Evaluate/Confirm the actual maximum performance of the accelerator
Propose the optimum scenario for the accelerator upgrade - imply forming task forces when needed to study specific subjects
Prepare WP (M+P), establish roadmap – EVM
Follow the procurement, tests and implementation of the changes
Prepare and commission the upgraded accelerator

## Slide 3: Organisation
Organisation
  Coordination meeting each 2 weeks
  Three working groups (ES beam dynamics and studies, JMJ ecloud mitigation, MM beam loss, TLs, protection)
  Advance in parallel, reduce meeting scope/length/attendance
  Continuity of people and activities
  Other working groups to be set up as needed/appropriate
Clear responsible for each implementation workunit
  Responsible for design studies, budget, manpower, planning, tracking, implementation
  Specifications to come (where needed) from study teams
  Reporting in coordination meeting

## Slide 4
Beam dynamics
Instabilities
Intensity limitation studies
Impedance
Longitudinal issues
Feedbacks
Simulations
Specifications
RF system upgrade
Wide bandwidth FB
e-cloud limits
Impedance upgrade
Instrumentation
e-cloud mitigation
Mitigation necessity
Surface treatments
Aging studies
Vacuum issues
Simulations
Specifications
Coating technology
Magnet chambers
Instrumentation
Beam loss, protection, TLs
Beam loss scenarios
Collimation studies
Scraper studies
Beam dump design
Extraction protection
TL and LHC injection protection
Specifications
Collimation system
Scraper upgrade
Beam dump
Instrumentation
Extraction diluters
TL protection devices
LIU-SPS coordination meeting
200 MHz RF
Magnet chamber e-cloud mitigation
Collimation system
Wide band feedback
Beam instrumentation (SPS and TLs)
RF low level control upgrade
ZS test area
Extraction diluters
Transfer line collimators
Scraper upgrade
Beam dump relocation/redesign
Further impedance reduction
New extraction kickers
ZS upgrade
Hardware and other implementation workpackages
Operational issues
Beam deployment
Radioprotection
General services
Powering
Layouts and DBs
Optics files
Integration
Planning
EVM, APT, MTP
Shutdown coordination
Consolidation
Safety, risk
E.Shaposhnikova
J.M.Jimenez
M.Meddahi
B.Goddard (deputy E.Shaposhnikova)
Update layout and optics DB
Update of drawings

## Slide 5: LIU-SPS project
ARDUINI,Gianluigi (BE-ABP-LIS)
ARGYROPOULOS,Theodoros (BE-RF-BR)
ARRUAT,Michel (BE-CO-FE)
ASSMANN,Ralph Wolfgang (BE-ABP-LCU)
BARNES,Mike (TE-ABT-FPS)
BARTMANN,Wolfgang (TE-ABT-BTP)
BARTOSIK,Hannes (BE-ABP-LIS)
BAUCHE,Jeremie (TE-MSC-MNC)
BAUDRENGHIEN,Philippe (BE-RF-FB)
BERRIG,Olav Ejner (BE-ABP-ICE)
BHAT,Chandrashekhara (BE-ABP)
BILLEN,Ronny (BE-CO-DM)
BOHL,Thomas (BE-RF-BR)
BORBURGH,Jan (TE-ABT-SE)
BURNS,Alan (BE-HDO)
CALATRONI,Sergio (TE-VSC-SCC)
CASPERS,Fritz (BE-RF-BR)
CHAPOCHNIKOVA,Elena (BE-RF-BR)
CHIGGIATO,Paolo (TE-VSC-IVM)
CORNELIS,Karel (BE-OP-SPS)
COSTA PINTO,Pedro (TE-VSC-SCC)
DUCIMETIERE,Laurent (TE-ABT-FPS)
ESTEBAN MULLER,Juan (BE-RF-BR)
FEDERMANN,Silke (BE-RF-BR)
FOLCH,Ramon (EN-MME)
GODDARD,Brennan (TE-ABT-BTP)
HOFLE,Wolfgang (BE-RF-FB)
JENSEN,Lars (BE-BI-SW)
JIMENEZ,Jose Miguel (TE-VSC)
KAIN,Verena (BE-OP-LHC)
LOSITO,Roberto (EN-STI)
MAHNER,Edgar (TE-VSC-IVM)
MANGLUNKI,Django (BE-OP-SPS)
MAURY CUNA,Humberto (BE-ABP-LCU)
MCFARLANE,David (EN-MEF-ABA)
MEDDAHI,Malika (TE-ABT-BTP)
METRAL,Elias (BE-ABP-ICE)
MISSIAEN,Dominique (BE-ABP-SU)
MONTESINOS,Eric (BE-RF-SR)
MUTTONI,Yvon (EN-MEF-INT)
PAPAPHILIPPOU,Yannis (BE-ABP-LIS)
PIERLOT,Jerome (EN-EL-BT)
RUEHL,Ingo (EN-HE)
RUMOLO,Giovanni (BE-ABP-ICE)
SALVANT,Benoit (BE-ABP-ICE)
TABORELLI,Mauro (TE-VSC-SCC)
TUCKMANTEL,Joachim (BE-RF-BR)
VINCKE helmut (DGS-RP-AS)
YIN VALLGREN,Christina (TE-VSC-SCC)

## Slide 6: Baseline for LIU-SPS
RF 200 MHz upgrade: completed for 2018
ecloud mitigation: aC coating: completed for 2018
New high bandwidth damper: completed for 2016
Existing damper power upgrade: completed for 2014
Beam instrumentation upgrades : completed for 2014
Scraper upgrade: completed for 2014
Extraction and TL protection upgrade: completed for 2015
MKE impedance reduction: completed for 2012
MKDV/H impedance reduction (transitions): completed for 2014
Beam dump design study: completed mid 2013
New MKE design study: completed mid 2013
Collimation design study: completed mid 2013
Transfer line protection design study: completed mid 2013

## Slide 7: Overall LIU WBS (agreed with groups)

## Slide 8
Checked with all group leaders
Introduced into EDMS and basis for budget codes

## Slide 9: MTP input – v1.0 finished
Budget

## Slide 10: MTP input – v1.0 finished
Manpower

## Slide 11: Work plan for 2011 (from LIU day)
Launch 200 MHz upgrade [OK – review finished]
  Technical decision mid 2011, civil engineering studies [to do]
Preparation for coating (4 half-cells, 1 sextant?) of SPS, or for clearing electrodes, or both? [OK – aC only, 1 electrode prototype]
  Decide on quadrupoles, pumping ports, other elements [to do]
  Big impact if long shutdown is moved to 2013 – more possible [OK]
High bandwidth feedback: studies, design report (LARP) [to do]
Define all additional BI upgrade requirements [OK – in progress]
Prepare 2 of final 3 MKE with serigraphy [OK – in progress]
  Problem if 2011/2012 shutdown less than 10 weeks [OK]
Launch full feasibility study for new MKE [to do]
  Including impedance calculations and benefit analysis
Key MDs defined for 2011? [OK – in progress]
  Low gamma transition optics
  High intensity single bunch to high intensity multibunch
  Making ‘ultimate’ intensity beams operational (50 and 75 ns?)
  Parameter limits for 25 ns spacing
  e-cloud mitigation validation
Additional points (since LIU day):
  Existing damper upgrade: requirements needed
  Scraper upgrade: requirements needed
  Beam loss control, machine protection and beam transfer: requirements needed
  Operational limitations: review and make sure all are being addressed