## Sheet1
| Time | SC composition | Objective | Participants | SC during LHC filling
MONDAY | 08:00-16:00 | MD_26_L25200_2012_V1 (25ns) | basic setup (Orbit, tunes, chromatcity, RF, feedback, …) | T. Argyropoulos, H. Bartosik, T. Bohl, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Salvant, E. Shaposhnikova, D. Valuch | MD_26_L25200_2012_V1 (25ns)
|  | + | preparation of ecloud measurements |  | +
LHC filling cycle
|  | LHCMD_50ns_D_2011_V1 (50ns) | e-cloud measurements with 50ns, standard intensity |  | +
CNGS?
| 16:00-05:00 | MD_26_L25200_2012_V1 (25ns) | ecloud build-up studies | T. Argyropoulos, H. Bartosik, T. Bohl, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Salvant, E. Shaposhnikova, D. Valuch
|  |  | estimation of liners and machine condition |  | MD_26_L25200_2012_V1 (25ns)
|  | + | more batches |  | +
|  |  | uncaptured beam |  | LHC filling cycle
|  |  | different beam conditions (find optimal scrubbing conditions) |  | +
|  | LHCMD_25ns_2011_V1 (25ns) | beam setup |  | CNGS?
TUESDAY | 08-10:30 | no beam | Intervention (electronics for vacuum gauges)
| 10:30-14:00 | MD_26_L25200_2012_V1 (25ns) | ecloud build-up studies | T. Argyropoulos, H. Bartosik, T. Bohl, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Slavant, E. Shaposhnikova, D. Valuch | MD_26_L25200_2012_V1 (25ns)
|  | + | more batches |  | +
|  |  | uncaptured beam |  | LHC filling cycle
|  |  | different beam conditions (find optimal scrubbing conditions) |  | +
|  | LHCMD_25ns_2011_V1 (25ns) | estimation of liners and machine condition |  | CNGS?
| 14:00-22:00 | MD_26_L25200_2012_V1 (25ns) -> COAST | Instabilities and transverse emittance blow-up | T. Argyropoulos, H. Bartosik, T. Bohl, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Salvant, E. Shaposhnikova, A. Ulsroed, D. Valuch | MD_26_L25200_2012_V1 (25ns)
|  |  | bunch-by-bunch BPMs |  | +
|  | maybe: | e-cloud measurements |  | LHC filling cycle
|  | MD_26_L25200_2012_V1_Q20 (25ns) | MW transmission measurements |  | +
|  |  | emittance measurements |  | CNGS?
| 22:00-08:00 | MD_26_L25200_2012_V1 (25ns) | Scrubbing as much as possible using the most effective beam | H. Bartosik, F. Caspers, M. Driss Mensi, S. Federmann, G. Iadarola, H. Neupert, G. Rumolo, M. Taborelli | MD_26_L25200_2012_V1 (25ns)
|  |  | uncaptured beam |  | +
|  | + | more than 4 batches |  | LHC filling cycle
+
|  | 2 x CNGS |  |  | CNGS?
WEDNESDAY | Wednesday | MD_26_L25200_2012_V1 (25ns) | Scrubbing with the most efficient beam conditions | H. Bartosik, F. Caspers, M. Driss Mensi, S. Federmann, G. Iadarola, H. Neupert, G. Rumolo, M. Taborelli | MD_26_L25200_2012_V1 (25ns)
| 08:00-22:00 |  | Stable beam conditions |  | +
|  | + | ecloud measurements |  | LHC filling cycle
|  |  | Clearing electrode voltage scan |  | +
|  | LHCMD_25ns_2011_V1 (25ns) | long drift chamber solenoid tests |  | CNGS?
| 22:00-08:00 | MD_26_L25200_2012_V1 (25ns) | Scrubbing with the most efficient beam conditions |  | MD_26_L25200_2012_V1 (25ns)
|  |  | Stable beam conditions for Mauro's measurements |  | +
|  | + | ecloud measurements |  | LHC filling cycle
+
|  | 2xCNGS |  |  | CNGS?
THURSDAY | Thursday | MD_26_L25200_2012_V1 (25ns) | Increase intensity from the PS | T. Argyropoulos, H. Bartosik, T. Bohl, H. Damerau, S. Hancock, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Salvant, E. Shaposhnikova, D. Valuch | MD_26_L25200_2012_V1 (25ns)
| 08:00-14:00 |  | optimize the cycles for higher intensity |  | +
|  | + | PS-SPS transmission studies |  | LHC filling cycle
+
|  | LHCMD_25ns_2011_V1 (25ns) |  |  | CNGS?
| 14:00-20:00 | MD_26_L25200_2012_V1 (25ns) | study e-cloud build-up and e-cloud instability with high intensity | T. Argyropoulos, H. Bartosik, T. Bohl, H. Damerau, S. Hancock, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Salvant, E. Shaposhnikova, D. Valuch | MD_26_L25200_2012_V1 (25ns)
+
|  | + |  |  | LHC filling cycle
+
|  | LHCMD_25ns_2011_V1 (25ns) |  |  | CNGS?
| 20:00-24:00 | coast with MD1 Q26 (25ns) | Emittance growth and instability studies | T. Argyropoulos, H. Bartosik, T. Bohl, H. Damerau, S. Hancock, W. Höfle, G. Iadarola, Y. Papaphilippou, G. Rumolo, B. Salvant, E. Shaposhnikova, A. Ulsroed, D. Valuch | MD_26_L25200_2012_V1 (25ns)
+
|  | maybe: |  |  | LHC filling cycle
|  | MD_26_L25200_2012_V1_Q20 (25ns) |  |  | +
CNGS?
| 24:00-08:00 | MD_26_L25200_2012_V1 (25ns) | continue scrubbing |  | MD_26_L25200_2012_V1 (25ns)
+
|  | + |  |  | LHC filling cycle
+
|  | 2 x CNGS |  |  | CNGS?
FRIDAY | Friday | MD_26_L25200_2012_V1 (25ns) | final measurements with 25ns beam | H. Bartosik, M. Driss Mensi, G. Iadarola, H. Neupert, G. Rumolo, M. Taborelli | MD_26_L25200_2012_V1 (25ns)
| 08:00-13:00 | + | machine and liners condition after scrubbing run |  | +
|  |  | threshold with 50ns beam |  | LHC filling cycle
|  | LHCMD_50ns_D_2011_V1 (50ns) |  |  | +
CNGS?
| 13:00-14:00 | no beam
| 14:00-15:00 |  | Intervention (electronics for vacuum gauges)
| 15:00 | beam back to physics

## Sheet3
Measurement/Task | Participants | Beam conditions | Time | Status/Comments
Setup nominal intensity 25ns and 50ns beams | H. Bartosik, G. Rumolo, Y. Papaphilippou (transverse), T. Argyropoulos, T. Bohl, J. Esteban Muller, E. Shaposhnikova, J. Tuckmantel (logitudinal), W. Hofle, D. Valuch (damper) |  | Monday
Setup high intensity 25ns and 50ns beams (possibly stepwise) | H. Damerau, S. Hancock (PS), H. Bartosik, G. Rumolo, Y. Papaphilippou (transverse), T. Argyropoulos, T. Bohl, J. Esteban Muller, E. Shaposhnikova, J. Tuckmantel (logitudinal), W. Hofle, D. Valuch (damper) | all | Thursday (Wednesday in the PS)
Bunch length meas. | T. Argyropoulos, J. Esteban Muller | all
High bandwidth pickup | H. Bartosik, W. Hofle, G. Iadarola, Y. Papaphilippou, G. Rumolo, A. Ulsroed | nominal 25, high intensity beams | Tuesday, Thurday
Strip detector with StSt liner | H.Bartosik, M. Driss Mensi, G. Iadarola, H. Neupert, M. Taborelli | nominal 25ns | all | some data collected on 08/03/2012
Strip detector with StSt liner and tungsten clearing electrode | M. Driss Mensi, H. Neupert, M. Taborelli | nominal 25ns | Wednesday | some data collected on 08/03/2012
Detector for slow electron measurements | B. Henrist | nominal 25ns |  | Setup is onging and will continue during the scrubbing run
Shielded pick-up | H. Bartosik, G. Iadarola, G. Rumolo | all | all | some data collected on 08/03/2012
Microwave transmission setup | F. Caspers, S. Federmann, R. M. Holz | all | Tuesday, Wendnesday, Thursday | Setup is onging
aC coated long drift chamber | M. Driss Mensi, H. Neupert, M. Taborelli | nominal 25ns | Wednesday | In place, access scheduled on Tuesday for electronics installation
Removable sample for SEY measurement | M. Driss Mensi, H. Neupert, M. Taborelli | all | Friday (access for removal) | In place, access scheduled on Friday for removal and transfer to lab for SEY meas.
Pressure measurements | M. Driss Mensi, H. Neupert, M. Taborelli | all | all
Local pressure increase in strip monitors | M. Driss Mensi, H. Neupert, M. Taborelli | nominal 25ns | Wednesday
Radial steering / Local orbit bump in ecloud monitors | H. Bartosik, G. Iadarola, G. Rumolo, OP | all | all
Wire scanner | H. Bartosik, A. Guerrero, G. Iadarola, G. Rumolo | all | all
FBCT | H. Bartosik, G. Iadarola, G. Rumolo | all | all