## Slide 1: Injector schedule and SPS MDs
G. Rumolo and H. Bartosik
LIU-SPS BD meeting, 26 June 2014
https://ab-mgt-md-users.web.cern.ch/ab-mgt-md-users/2014/index.html

## Slide 2: Machine start up, scrubbing and beginning of MDs v1.3
Start of MDs @SPS
Scrubbing run
Scrubbing run
96h dedicated MD time @SPS + 2 x 24h UA9
12h slots instead of 10h: to recover the MD time lost for the Technical stop (week 44)
 agreed with physics coordinator and MSWG

## Slide 3: Splitting the SPS scrubbing run
  SPS restart and MD program in 2014 is extremely ambitious + SPS must also do many other things in parallel, including making the ‘doublet’ scrubbing beam operational for LHC and many other operational and MD beams
  (LIU-SPS Coordination Meeting , 2 April, 2014)
  As outcome of the Evian workshop, Brennan proposed to split the scrubbing period in two weeks (second week around end of October/start of November)
  Official request from LIU-SPS submitted to physics coordinator to split the scrubbing run in order to increase the chances of success in several ways:
    Allowing time to analyse the first week’s results and adapt/resimulate accordingly;
    Untangling the 2nd week from the machine commissioning and NA setup;
    Allowing tests with the ‘doublet’ beam before the 2nd scrubbing week in parallel MD, so that it might even be available to scrub the SPS;
    Allowing work on the high intensity LHC beam in parallel MD, to increase the quality;
    Giving more time for vacuum conditioning of all the newly-installed or vented equipment;
    Avoiding the present overlap with the Chamonix workshop which presently clashes completely.
  No extra time is requested from physics. Drawback  a rescheduling of 1 week of the NA program is required

## Slide 4: Machine start up, scrubbing and beginning of MDs v1.4
Scrubbing run
Scrubbing run
Start of MDs @SPS
96h dedicated MD time @SPS + 2 x 24h UA9
Wednesday slots to be moved: from 06:00-18:00 to avoid shift handover and late machine recovery after MDs

## Slide 5: MD requests: SPS
Parallel MDs (I)
  Test of new SPS BQM (G. Papotti)
  Longitudinal impedance (E. Shaposhnikova et al)  single bunch on Q26, scanning longitudinal emittance in small steps
  Longitudinal space charge (E. Shaposhnikova et al)  need intermediate flat portion
  Microwave instability (E. Shaposhnikova et al)
  Instability threshold due to the S shape of the injected bunch (E. Shaposhnikova et al.)
  Check behavior of LHC BPMs with doublet beams by means of controlled orbit bumps to extrapolate error to LHC (T. Lefèvre, E. Calvo)
  Transverse feedback systems (W. Höfle et al):
    Normal damper  commissioning should be done during first two weeks of set up with beam
    High bandwidth damper  MDs will take place mainly during the scrubbing run and then later during MDs with 25 ns or doublet beams

## Slide 6: MD requests: SPS
Parallel MDs (II)
  Transverse impedance measurements (H. Bartosik, N. Biancacci, C. Zannini)
    Tune shift vs intensity
    Growth times with chromaticity
    TMCI thresholds
    Impedance localization
  Transverse space charge, explore tune space with ultra-bright beams (H. Bartosik)
  Set up of Ar cycle for 2015 (T. Bohl, D. Manglunki)
  AWAKE synchronization tests (T. Bohl)  initially without beam
  Emittance preservation across injection chain (G. Sterbini, A. Guerrero)
Requested MD time amounts to about 8 weeks (4 days per week – excluding Wednesdays) out of the 9 available weeks

## Slide 7: MD requests: SPS
Dedicated MDs
  Optimization of both 50 ns (1.7e11 ppb) and 25 ns (1.2e11 ppb) beams and recovery of 2012 performances (LIU-SPS)
  Recover doublet beam production and set up of acceleration to 450 GeV (H. Bartosik, G. Iadarola, et al)
    Requires new magnetic cycle with slow ramp
  800 MHz commissioning with beam (E. Shaposhnikova et al)
    1 session at beginning of run, 2 after performance recovery
  Coupled bunch instability (E. Shaposhnikova et al)  studies with different numbers of bunches and scanning bunch intensity
  Test of 8b + 4e scheme (LIU-SPS)
  Test controls for the collimation alignment with in-jaw BPMs (collimation team)
  Qualification of sponge materials on UA9 goniometer (UA9 team)
  Emittance growth for crab cavity tests (R. Calaga)

## Slide 8: MD requests: SPS
Dedicated MDs
Requested MD time amounts to about 160h out of the presently available 96h (8 x 12h blocks)
Calculated MD time does not include set up of the coasting cycles, which in previous years took at least one shift per type of coasting cycle
However:
  16h emittance growth could be shifted to 2015 (R. Calaga confirmed)
  8b+4e probably also not available before 2015 (8h)
  4h UA9 anyway not available as TS after UA9 run
  24h considered for performance recovery (50 and 25 ns), could also be done in parallel as machine commissioning
  Collimator MD could take 2 instead of the requested 3 shifts
  100h remaining for 2014, which would only exceed the available hours by 4h

## Slide 9: SPS MDs – miscellaneous
MD cycles
  The required MD cycles need to be planned and known well in advance, since Stephane Cettour Cave is only authorized to prepare new cycles after approval of Karel (MSWG, May 30, 2014)
  Parallel MD time
  The parallel MD time (including set up for the Ar ion physics) for the moment does not include possible additional time needed for the set up of new cycles (e.g. the coasting cycles)
  Constraints from the Ar beam setup:
    RF setting-up of the parallel ion cycle in the SPS is not compatible with any RF measurements at another parallel cycle in the same SC
    Initial phase of the setup: 4 days/week for 8h during day time (for at least 2 weeks)
    This will be followed for some time with having the cycle twice per week on consecutive days for 8h during daytime
    one day per week is a general dedicated MD

## Slide 10: Summary
SPS scrubbing runs(s) in 2014:
  Originally two weeks at end of September / beginning of October
  Official request from LIU-SPS to split the scrubbing run in two parts to increase chances of success in many aspects + allow to test the scrubbing with the doublet beam in the SPS
  Present planning: 1 week end of September + 1 week beginning of November
SPS MDs in 2014
  SPS MDs will start in Week 41 after the first scrubbing week
  Dedicated MDs on Wednesdays 12h (most likely from 06:00-18:00 to avoid shift handover and late machine recovery after MDs)
MD Requests vs available time
  Parallel MD time will be hopefully enough
  About 160h requested for dedicated MDs out of 96h available, however situation could be handled