## Slide 1: LIU SPS beam dynamics topics and milestones
H. Bartosik, E. Shaposhnikova for the LIU SPS beam dynamics WG
LIU -PS beam dynamics WG meeting, 28 March 2019

## Slide 2: LIU SPS BD - Topics and milestones 2019/20
Transverse
  Further analysis for input for decision on installation of new flanges at QD-MBB transition for momentum aperture fix (doubt on results)  Planned for LIU-SPS TC (Stephane Cettour-Cave to come with the VSC guys, will involve requests for moving MBBs etc.)
  Benchmarking of bunch-by-bunch tune shift measurements with impedance model (and contributions from electron cloud)  in 2019
  Horizontal instability at SPS injection (coupled bunch impedance, electron cloud) - source to be identified to prepare mitigation strategy and future actions (data analysis and simulation studies)  first results in 2019, conclude in 2020
  Impact of bunch-by-bunch tune shift on incoherent tune footprint of different bunches for working point optimization  long-term
  Emittance preservation studies in view of operation with -0.21 space charge tune shift (LIU BCMS) on top of bunch-by-bunch tune shifts from impedance (effect of tune ripple on transverse emittance growth)  long-term
  Simulate TMCI thresholds for LIU brightness in Q20 and LIU intensity, also with smaller longitudinal emittance  long term
  Check if transverse instabilities to be expected during slip stacking  before end 2020

## Slide 3: LIU SPS BD - Topics and milestones 2019/20
Longitudinal
  Beam dynamics input for decision on installation of 630 MHz HOM damper (estimate effect of shift of fundamental mode plus technical risks)  May 2019
  Quality control of impedance reduction (VF shielding) in the tunnel  Procedure agreed and review by start of works (date to confirm with Paul)
  Longitudinal instability on the ramp including impact of smaller longitudinal emittance  Q1 2020
  Study the impact of installing 200 MHz cavities for eSPS on proton beam stability  end 2019 (manpower to obtain from PBC/CLIC)
  Beam losses on flat bottom and at the beginning of ramp (full bucket due to PS bunch distribution) together with feasibility of smaller longitudinal emittance  06.2019
  Study and propose mitigation of longitudinal instabilities for ions  06.2019
  Definition of slip stacking scenario  end 2020

## Slide 4: LIU milestones related to the SPS BD WG
May-19 | BD input for decision on installation of 630 MHz HOM damper | BE-RF
Jun-19 | Review 200 MHz overall progress, including 200 MHz HOM decision | LIU SPS JTL
Dec-19 | Beam loss on FB/ start ramp + feasibility of smaller longitudinal emittance | BE-RF
Dec-19 | Horizontal instability - first results on source + possible mitigations | BE-ABP
Dec-19 | Impact of bunch-by-bunch tune shift on tune footprint of bunches | BE-ABP
Sep-20 | Horizontal instability - conclude on effect and strategy for mitigation | BE-ABP, BE-RF
Sep-20 | Study and propose mitigation of longitudinal instabilities for ions | BE-RF
Dec-20 | Definition & performance of slip stacking scenario | BE-RF
Dec-20 | Emittance preservation for operation with -0.21 space charge tune shift | BE-ABP
Dec-20 | Transverse instabilities to be expected during slip stacking | BE-ABP, BE-RF