## Slide 1: SPS vacuum modification
G.Vandoni

## Slide 2: Summary
Open issues
Modifications
Shutdown workflow
Procedures
Vacuum layout
Equipment
Summary
What I expose here is the pot-pourri of possible modifications, the next step would be to establish a ranking and prioritize studies.

## Slide 3: Some open issues
Ageing upon air exposure:
Rough-pumping VS dry air or N2 venting
Allowed time for air exposure? interdiffusivity
Limited time for preliminary study: definition of well controlled procedures to permit post-mortem study & diagnostics
What amount of coating is necessary <100%
Interdiffusion coeff ~1m2/s, front progression

## Slide 4: Shutdown workflow
Today
Tomorrow
Equipment disconnected at the start, reconnected at the end
  BI instrumentation, magnets, septa…
Alignment (tilt!) before connection
Parallel work on several sectors: optimization of resources and equipment
Slow transport engines, several magnets treated on each sector
Immediate replacement upon disconnection OR rough pumping
Closure and pumping before alignment, then reopening.
Each sector is treated in a go: increased manpower and equipment.
Any delay in transport may limit access in the tunnel (engine parked in-situ).

## Slide 5: Procedures*
Today
Tomorrow
Plug-in equipment is transported, aligned, connected exposed to atmosphere
Magnet’s interchangeability, upon modification in situ of pumping port shielding to adapt to vacuum chamber’s length
Substitution of heavy equipment by use of same engine (back and forth)
Storage, transport of magnets opened or mechanically protected
SPS Vacuum modification, G.Vandoni @SPSU
5
Connection under dry air or N2 flood.
To speed up replacement, magnets come back at the same place, or N2 flow during pps modification
As soon as an element is disconnected, the spare is connected or the 2 sector halves are rough-pumped
Storage, transport of magnets under vacuum or N2
*History control/post-mortem diagnostics

## Slide 6: Vacuum and mechanical layout
Today
Tomorrow
Experimental equipment in vacuum sectors
Quadrupoles are references for alignment
Multiplication of “phantom valves”? See above
If quadrupoles are to be coated, a survey study is necessary for ways to shorten subsequent alignment process
No necessity to refine sectorization:
Long sectors would be briefly closed by blank flanges (like LHC)
Delicate equipment, submitted to long air exposure, is already separated (back to “what amount of coating”?)

## Slide 7: Equipment
Study a new design of pumping ports to allow for alignement when closed, with pumping port shielding and sabre inserted, thin covers with N2 venting and rough-pumping port
Mobile, rough-pumping stations, monitoring needs and methods to study
Study required for alignement equipment and procedures
Study required for transport engines

## Slide 8: To conclude
For vacuum, required actions are
  Shutdown workflow and related manpower
  Installation procedures (dry air flow, pumpdown)
  Design of standard pumping port and closing flanges
  Mobile pumping groups
  Monitoring?
Some analysis required from other groups: survey, transport, equipment groups
Next step should be a ranking of necessary study